## Summary
Project Performance Summary
Inputs
Budget at Completion (BAC) | 240000 | Source: approved project budget (fictional example)
Status period (1–8) | 6 | Change to see performance at any reported period
Values at status period
Planned Value (PV) | 180000 | Value of work planned to date
Earned Value (EV) | 160000 | Value of work actually completed
Actual Cost (AC) | 185000 | What the completed work actually cost
Performance
Cost Variance (CV) | -25000 | EV − AC (negative = over budget)
Schedule Variance (SV) | -20000 | EV − PV (negative = behind schedule)
Cost Performance Index (CPI) | 0.86486 | EV ÷ AC (below 1 = over budget)
Schedule Performance Index (SPI) | 0.88889 | EV ÷ PV (below 1 = behind schedule)
Forecast
Estimate at Completion (EAC) | 277500 | BAC ÷ CPI (if current cost performance continues)
Estimate to Complete (ETC) | 92500 | EAC − AC
Variance at Completion (VAC) | -37500 | BAC − EAC (negative = expected overspend)
To-Complete Performance Index (TCPI) | 1.4545 | Efficiency needed on remaining work to finish on budget
Status
Cost status | Red | Green ≥ 0.95 · Amber ≥ 0.90 · Red < 0.90
Schedule status | Red | Green ≥ 0.95 · Amber ≥ 0.90 · Red < 0.90

## EVM Data
Earned Value Tracker — Restaurant POS Upgrade (fictional example)
Cumulative values in GBP. Blue cells are inputs; black cells are formulas. Leave EV and AC blank for future periods.
Period | Month | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Cost Variance (CV) | Schedule Variance (SV) | CPI | SPI
1 | Jan | 20000 | 18000 | 21000 | -3000 | -2000 | 0.85714 | 0.9
2 | Feb | 45000 | 40000 | 47000 | -7000 | -5000 | 0.85106 | 0.88889
3 | Mar | 75000 | 66000 | 77000 | -11000 | -9000 | 0.85714 | 0.88
4 | Apr | 110000 | 98000 | 112000 | -14000 | -12000 | 0.875 | 0.89091
5 | May | 145000 | 130000 | 148000 | -18000 | -15000 | 0.87838 | 0.89655
6 | Jun | 180000 | 160000 | 185000 | -25000 | -20000 | 0.86486 | 0.88889
7 | Jul | 215000
8 | Aug | 240000

## How to Use
How to use this tracker
1. On 'EVM Data', enter cumulative Planned Value (PV) for every period from the baseline plan.
2. Each reporting period, enter cumulative Earned Value (EV) and Actual Cost (AC). Leave future periods blank.
3. On 'Summary', set the status period. All variances, indices, forecasts and RAG statuses update automatically.
Colour key: blue text = input you edit · black text = formula · yellow fill = key assumption.
Earned Value = % of work complete × budget for that work (BAC).
All figures are illustrative and belong to a fictional example project.